## Product Recommendation
PRODUCT RECOMENDATION TIMELINE | [8 empty] | 12 | 2024-05-27 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
[10 empty] | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23
TASK ID | TASK TITLE | NOTE | TASK OWNER | DOD | START DATE | DURATION | END DATE | TIME LEFT | STATUS | 2024-05-20: WEEK 12 (20/05 - 26/05); 2024-05-27: WEEK 13 (27/05 - 02/06); 2024-06-03: WEEK 14 (03/06 - 09/06); 2024-06-10: WEEK 15 (10/06 - 16/06); 2024-06-17: WEEK 16 (17/06 - 23/06)
[10 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
A. | SYSTEM DEFINITION |  | Đạt |  | 2024-03-18 | 45 | 2024-05-17 | Expired | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
1.1 | Research high-level algorithms of up-sell/cross-sell products recommendation model |  | Đạt |  | 2024-03-15 | 2 | 2024-03-18 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Write requirement |  | Đạt |  | 2024-03-19 | 1 | 2024-03-19 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.3 | Design model architecture |  | Đạt |  | 2024-03-21 | 1 | 2024-03-21 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.4 | Setup resources & environments |  | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
B. | DATA PREPARATION |  | Đạt |  | 2024-05-20 | 10 | 2024-05-31 | 1 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
1 | List data requirement | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2 | Preprocess the news articles | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
C. | DATA PROCESSING |  | Đạt |  | 2024-06-24 | 30 | 2024-08-02 | 64 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
D. | MODEL DEVELOPMENT |  | Đạt |  | 2024-08-05 | 20 | 2024-08-30 | 92 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
E. | MODEL DEPLOYMENT |  | Đạt |  | 2024-08-05 | 20 | 2024-08-30 | 92 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
F. | MONITORING & MAINTAIN |  | Đạt |  | 2024-08-05 | 20 | 2024-08-30 | 92 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 16 (17/06 - 23/06) Su
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦

## News system
NEWS SYSTEM PLAN | [8 empty] | 12 | 2024-05-27 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2024-05-20 to 2024-07-14
TASK ID | TASK TITLE | NOTE | TASK OWNER | SPRINT | START DATE | DURATION | END DATE | TIME LEFT | STATUS | 2024-05-20: WEEK 12 (20/05 - 26/05); 2024-05-27: WEEK 13 (27/05 - 02/06); 2024-06-03: WEEK 14 (03/06 - 09/06); 2024-06-10: WEEK 15 (10/06 - 16/06); 2024-06-17: WEEK 16 (17/06 - 23/06); 2024-06-24: WEEK 17 (24/06 - 30/06); 2024-07-01: WEEK 18 (01/07 - 07/07); 2024-07-08: WEEK 19 (08/07 - 14/07)
[10 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
A. | NEWS AI CLASSIFICATION |  | Đạt |  | 2024-03-18 | 45 | 2024-05-17 | Expired | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  | 2024-03-15 | 2 | 2024-03-18 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Design model architecture | 1. Training: Components + GCP service + algorithms + backtest pipeline 2. Deploy + production: Data pipeline + platform + dockerize + monitoring 3. Tuning model pipeline | Đạt |  | 2024-03-19 | 1 | 2024-03-19 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.3 | Plan how to labeling news data for classification model |  | Đạt |  | 2024-03-21 | 1 | 2024-03-21 | Done | Done | bar: WEEK 13 (27/05 - 02/06) F
1.4 | Setup resources & environments |  | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
2.1 | Data collection |  | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation | contents, labels (classification), title, tags, categories, brief | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles | tokenization, removing stop words, and stemming | Đạt |  | 2024-04-01 | 4 | 2024-04-04 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles - write method and plan |  | Đạt |  | 2024-03-26 | 1 | 2024-03-26 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.1 | - by category | refactor category | Đạt |  | 2024-03-27 | 3 | 2024-03-29 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.2 | - by sector | manual labeling | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.3 | - by sentiment | manual labeling | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
3.1 | Data train/test split |  | Đạt |  | 2024-04-04 | 1 | 2024-04-04 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data loader pipeline |  | Đạt |  | 2024-04-04 | 2 | 2024-04-05 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data preprocessing |  | Đạt |  | 2024-04-08 | 4 | 2024-04-11 | Expired | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Build classification model - by category |  | Đạt |  |  | 7 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4.1 | - Build architecture |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4.2 | - Train model |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4.3 | - Evaluation model |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4.4 | - Tuning model |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4.5 | - Ensemble model |  | Đạt |  |  | 0 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6.2 | - Train model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
3.6.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (27/05 - 02/06) F
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
4.1 | Dockerize model |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Monitor system |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
B. | CUSTOMER PREFERENCES |  | Đạt |  | 2024-05-20 | 25 | 2024-06-21 | 22 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
C. | NEWS RECOMMENDATION |  | Đạt |  | 2024-06-24 | 30 | 2024-08-02 | 64 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
C. | NEWS SUMMARIZER |  | Đạt |  | 2024-08-05 | 20 | 2024-08-30 | 92 days | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (20/05 - 26/05) M to WEEK 19 (08/07 - 14/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (27/05 - 02/06) F
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
Note on C8: Khong Tien Dat: 1. Training: Components + GCP service + algorithms + backtest pipeline 2. Deploy + production: Data pipeline + platform + dockerize + monitoring 3. Tuning model pipeline

## Costs (hidden)
Stt | Mục | Nội dung | Chi tiết | Địa điểm | Chi phí | PIC | Timeline | Status | Note |  | Cost | 84150 | 76500 | 7650
1 | Trang phục | Nhẫn cưới |  |  | 15000 | Done |  |  |  |  | Quỹ | 51800 | -32350
|  | Trang sức |  |  | 1000 | Liên | 2024-03-22 |  |  |  | 30000 | Near
|  | Thuê áo dài bế tráp |  |  | Trong gói chụp ảnh cưới | Liên | 2024-03-09 |  |  |  | 10000 | lương đạt t2
|  | Thuê áo dài cô dâu chú rể |  |  | Trong gói chụp ảnh cưới | Liên | 2024-03-09 |  |  |  | 11800 | Quỹ
|  | Váy nhẹ nhàng tiếp khách cho cô dâu + giày |  |  | 1700 | Liên | 2024-03-29 |  | Hỏi chị phương
|  | sơ mi cho chú rể | Cần chuẩn bị |  | 500 | Liên | 2024-03-09 |  | hỏi hiền linh
|  | Váy cưới cô dâu |  |  | Trong gói chụp ảnh cưới | Liên | 2024-03-09
|  | Vest chú rể |  |  | 3000 | Liên/Đạt | 2024-03-09 |  | Tìm chỗ mua vest backup
|  | Giày chú rể |  |  | Trong gói chụp ảnh cưới/may | Liên/Đạt | 2024-03-09 |  | Tìm chỗ mua vest backup
|  | Làm tóc |  |  | 500 | Liên/Đạt | 2024-03-20 |  | hỏi hiền linh xem có cần làm tóc không hay thuê làm tóc
|  | Làm nail |  |  | 500 | Liên
2 | Chụp ảnh/video cưới | Chụp ảnh cưới |  |  | 12800 | Liên | 2024-03-09
|  | Chụp ăn hỏi |  |  | 15000 | Liên | 2024-03-08 |  | Hỏi hiền linh
|  | Phóng sự cưới nhà gái |  |  | trong chụp ăn hỏi | Liên | 2024-03-08 |  | Hỏi hiền linh
|  | Phóng sự cưới nhà trai |  |  | trong chụp ăn hỏi | Đạt | 2024-03-08 |  | prefer 1 team cho cả nhà trai và nhà gái, hỏi hiền linh và chị phương
3 | Thuê make-up | Ăn hỏi |  |  | 2000 | Liên | 2024-03-12 |  | Thuê makeup trước
|  | Hôm cưới |  |  | 2200 | Liên | 2024-03-12 |  | Thuê makeup trước
4 | Mời khách | Lên danh sách |  |  | 0 | Liên/Đạt | 2024-03-17
|  | Thiệp mời |  |  | 4000 | Đạt | 2024-03-17
|  | Ảnh cho đám cưới |  |  | 1000 | Đạt | 2024-04-21
|  | Wedding page |  |  | 0 | Đạt | 2024-04-07
|  | Xe đưa đón về NB |  |  | 2700 | Liên | 2024-04-20
|  | Xe đưa đón về HD |  |  | 2700 | Đạt | 2024-04-20
|  | Nhà nghỉ |  |  | 2000 | Đạt | 2024-04-23
|  | Bữa mời cưới |  |  | 5000 | Liên/Đạt | 2024-04-14
5 | Dạm ngõ | Chuẩn bị bữa ăn nhà trai sang |  |  | 0 | Liên | 2024-03-03 | Done | Ở nhà, Anh trai chuẩn bị mâm cơm
|  | Thuê xe sang nhà trai |  |  | 0 | Liên | 2024-03-15 |  | Anh trai chuẩn bị
6 | Lễ ăn hỏi | Tiền lì xì |  |  | 1400 | Liên | 2024-04-24 |  | 100K-200K/lì xì, hỏi người có kinh nghiệm | 2100
|  | Thuê đội bê tráp |  |  | 1500
7 | Lễ cưới | Xe đón dâu |  |  | 0 | Đạt | 2024-04-16
|  | Xe đưa dâu |  |  | 0 | Liên | 2024-04-23 |  | Anh trai chuẩn bị
8 | Đi lại |  |  |  | 2000