## Product Recommendation
| PRODUCT RECOMENDATION TIMELINE | [8 empty] | 12 | 2024-06-03 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
 | time axis 2024-05-27 to 2024-07-14
| TASK ID | TASK TITLE | DOD | NOTE | TASK OWNER | START DATE | DURATION | END DATE | TIME LEFT | STATUS | 2024-05-27: WEEK 12 (27/05 - 02/06); 2024-06-03: WEEK 13 (03/06 - 09/06); 2024-06-10: WEEK 14 (10/06 - 16/06); 2024-06-17: WEEK 15 (17/06 - 23/06); 2024-06-24: WEEK 16 (24/06 - 30/06); 2024-07-01: WEEK 16 (01/07 - 07/07); 2024-07-08: WEEK 16 (08/07 - 14/07)
[11 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
1 | 1 | MODEL DEFINITION |  |  | Đạt | 2024-05-27 | 6 | 2024-06-03 | 1 days | Doing | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 1.1 | Define Requirements & Architecture |  |  |  | 2024-05-27 | 6 | 2024-06-03 | 1 days | Doing | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 1.1.1 | Research high-level algorithms of up-sell/cross-sell products recommendation model |  |  | Đạt | 2024-05-27 | 2 | 2024-05-28 | Done | Done | bar: WEEK 13 (03/06 - 09/06) M
3 | 1.1.2 | Write requirement |  |  | Đạt | 2024-05-29 | 3 | 2024-05-31 | Done | Done | bar: WEEK 13 (03/06 - 09/06) M
3 | 1.1.3 | Design model architecture |  |  | Đạt | 2024-06-03 | 1 | 2024-06-03 | 1 days | Doing | bar: WEEK 13 (03/06 - 09/06) M
3 | 1.1.4 | Setup resources & environments |  |  | Đạt | 2024-06-03 | 1 | 2024-06-03 | 1 days | Doing | bar: WEEK 13 (03/06 - 09/06) M
1 | 2 | DATA PREPARATION |  |  | Đạt | 2024-06-04 | 9 | 2024-06-14 | 12 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 2.1 | List data requirement |  |  |  | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 2.1.1 | Write data collection requirements |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 2.2 | Write data collection check-list |  |  |  | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 2.2.1 | Customer data |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.2.2 | Stock data |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.2.3 | Bond data |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.2.4 | Derivative data |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.2.5 | Market data |  |  | Đạt | 2024-06-04 | 1 | 2024-06-04 | 2 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 2.3 | Data collection: Customer data |  |  |  | 2024-06-05 | 5 | 2024-06-11 | 9 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 2.3.1 | Define the schema of the customer data table |  |  | Đạt | 2024-06-05 | 1 | 2024-06-05 | 3 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.3.2 | Write load pipeline code |  |  | Đạt | 2024-06-05 | 5 | 2024-06-11 | 9 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | 2.3.2.1 | - Person Infomation |  |  | Đạt | 2024-06-05 | 1 | 2024-06-05 | 3 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.3.3 | Write data dictionary |  |  | Đạt | 2024-06-11 | 1 | 2024-06-11 | 9 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.3.4 | Get data example follow requirements |  |  | Đạt | 2024-06-11 | 1 | 2024-06-11 | 9 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 2.4 | Data collection: Stock data |  |  |  | 2024-06-12 | 3 | 2024-06-14 | 12 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 2.4.1 | Define the schema of the stock data table |  |  | Đạt | 2024-06-12 | 1 | 2024-06-12 | 10 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.4.2 | Write Load pipeline code |  |  | Đạt | 2024-06-12 | 3 | 2024-06-14 | 12 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.4.3 | Write data dictionary |  |  | Đạt | 2024-06-14 | 1 | 2024-06-14 | 12 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 2.4.4 | Get data example follow requirements |  |  | Đạt | 2024-06-14 | 1 | 2024-06-14 | 12 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 2.5 | Data collection: Bond data | [6 empty] | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 2.6 | Data collection: Derivative data | [6 empty] | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 2.7 | Data collection: Market data | [6 empty] | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
1 | 3 | DATA PROCESSING & EDA |  |  | Đạt | 2024-06-17 | 5 | 2024-06-21 | 19 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 3.1 | Clean Data |  |  |  | 2024-06-17 | 3 | 2024-06-19 | 17 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 3.1.1 | Handle missing values |  |  | Đạt | 2024-06-17 | 2 | 2024-06-18 | 16 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 3.1.2 | Remove duplicates |  |  | Đạt | 2024-06-18 | 1 | 2024-06-18 | 16 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 3.1.3 | Correct data types |  |  | Đạt | 2024-06-19 | 1 | 2024-06-19 | 17 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 3.2 | EDA |  |  |  | 2024-06-20 | 2 | 2024-06-21 | 19 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 3.2.1 | Analyze Customer Data | Understand the distribution, trends, and patterns in customer preferences. |  | Đạt | 2024-06-20 | 1 | 2024-06-20 | 18 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 3.2.2 | Analyze Stock Data | Identify key characteristics of stocks that can influence recommendations. |  | Đạt | 2024-06-20 | 1 | 2024-06-20 | 18 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 3.2.3 | Analyze Trading Data | Look for patterns in customer trading behavior. |  | Đạt | 2024-06-21 | 1 | 2024-06-21 | 19 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
1 | 4 | MODEL DEVELOPMENT |  |  | Đạt | 2024-06-24 | 13 | 2024-07-10 | 38 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 4.1 | Model Predevelopment |  |  |  | 2024-06-24 | 1 | 2024-06-24 | 22 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.1.1 | Data train/test split |  |  | Đạt | 2024-06-24 | 1 | 2024-06-24 | 22 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.1.2 | Setup config and global parameters |  |  | Đạt | 2024-06-24 | 1 | 2024-06-24 | 22 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.2 | Feature Engineering |  |  |  | 2024-06-24 | 3 | 2024-06-26 | 24 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.2.1 | Create new features from existing data |  |  | Đạt | 2024-06-24 | 2 | 2024-06-25 | 23 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.2.2 | Normalize or standardize features if necessary. |  |  | Đạt | 2024-06-26 | 1 | 2024-06-26 | 24 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.3 | Feature Selection |  |  |  | 2024-06-27 | 2 | 2024-06-28 | 26 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.3.1 | Correlation Analysis | Compute the correlation matrix to identify highly correlated features. Remove one of each pair of highly correlated features to reduce redundancy. |  | Đạt | 2024-06-27 | 1 | 2024-06-27 | 25 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.3.2 | Statistical Tests | Use statistical tests (e.g., chi-square, ANOVA) to evaluate the significance of each feature. Retain features with high statistical significance. |  | Đạt | 2024-06-27 | 1 | 2024-06-27 | 25 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.3.3 | Select Feature |  |  | Đạt | 2024-06-28 | 1 | 2024-06-28 | 26 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.3.4 | Feature Importance from Models | Train a simple model (e.g., random forest, decision tree) to assess feature importance. Use the feature importance scores to select the most relevant features. |  | Đạt | 2024-06-28 | 1 | 2024-06-28 | 26 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.3.5 | Recursive Feature Elimination (RFE) | Use RFE with a model to recursively remove least important features. Continue until a desired number of features is reached. |  | Đạt | 2024-06-28 | 1 | 2024-06-28 | 26 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.3.6 | Principal Component Analysis (PCA) | Apply PCA to reduce dimensionality while retaining most of the variance. Use the principal components as features for the recommendation model. |  | Đạt | 2024-06-28 | 1 | 2024-06-28 | 26 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.4 | Collaborative Filtering Model |  |  |  | 2024-07-01 | 4 | 2024-07-04 | 32 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.4.1 | Compute similarity matrices |  |  | Đạt | 2024-07-01 | 1 | 2024-07-01 | 29 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.4.2 | Training model |  |  | Đạt | 2024-07-02 | 2 | 2024-07-03 | 31 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | 4.4.2.1 | - Based on similar users |  |  | Đạt | 2024-07-02 | 1 | 2024-07-02 | 30 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | 4.4.2.2 | - Based on similar items |  |  | Đạt | 2024-07-03 | 1 | 2024-07-03 | 31 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.4.3 | Model Evaluation |  |  | Đạt | 2024-07-04 | 1 | 2024-07-04 | 32 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.5 | Content-Based Filtering |  |  |  | 2024-07-05 | 3 | 2024-07-09 | 37 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.5.1 | Create a profile for each customer |  |  | Đạt | 2024-07-05 | 1 | 2024-07-05 | 33 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.5.2 | Match stock attributes to customer profiles. |  |  | Đạt | 2024-07-05 | 1 | 2024-07-05 | 33 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.5.3 | Model Evaluation |  |  | Đạt | 2024-07-08 | 1 | 2024-07-08 | 36 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.6 | Hybrid Approach |  |  |  | 2024-07-10 | 1 | 2024-07-10 | 38 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 4.6.1 | Weighting each sub-model |  |  | Đạt | 2024-07-10 | 1 | 2024-07-10 | 38 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 4.6.2 | Generate recommendations in hybrid |  |  | Đạt | 2024-07-10 | 1 | 2024-07-10 | 38 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 4.7 | Neural Network Recommendation |  | [Fully connected layer](https://phamdinhkhanh.github.io/2019/12/26/Sorfmax_Recommendation_Neural_Network.html) |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
1 | 5 | MODEL DEPLOYMENT |  |  | Đạt | 2024-07-11 | 2 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 5.1 | API development (optional) | [6 empty] | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 5.1.1 | Define API Requirements |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.2 | Choose an API Framework |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.3 | Develop the API | Define API Endpoints: Implement the logic for each endpoint, including request handling and response generation. Implement Authentication: Integrate authentication mechanisms to secure access to the API endpoints. Implement Data Validation: Validate input data to ensure its integrity and prevent security vulnerabilities like SQL injection or XSS attacks. Handle Errors: Implement error handling logic to return appropriate HTTP status codes and error messages for different scenarios. |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.4 | Test the API Locally | Unit Testing: Write and execute unit tests to verify the functionality of individual API endpoints. Integration Testing: Test the API as a whole, including interactions between different endpoints and components. Mocking: Use mocking frameworks to simulate external dependencies and isolate the API for testing. |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.5 | Deploy the API to GCP | Containerization: Containerize the API using Docker to create a portable and consistent deployment artifact. Google Kubernetes Engine (GKE): Deploy the containerized API to GKE, a managed Kubernetes service on GCP, for scalable and reliable execution. Serverless Options: Alternatively, you can deploy serverless APIs using Google Cloud Functions or Google App Engine, which abstract away infrastructure management. |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.6 | Configure API Gateway and Services |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.1.7 | Build log system + monitoring |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 5.2 | Integration with BigQuery |  |  |  | 2024-07-11 | 2 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 5.2.1 | Design output table in bigquery |  |  | Đạt | 2024-07-11 | 1 | 2024-07-11 | 39 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.2.2 | Build pipeline to save the output model to BQ |  |  | Đạt | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.2.3 | Test pipeline |  |  | Đạt | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 5.3 | Scalability with batch processing (optional) | [6 empty] | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 5.4 | Dockerize model | [6 empty] | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 5.4.1 | Write docker file |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.4.2 | Dockerize model |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.4.3 | Deploy docker to GCP |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.4.4 | Config docker |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.4.5 | Run test docker |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 5.5 | Tesing & run One-time sample |  |  |  | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 5.5.1 | Full pipeline testing |  |  | Đạt | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.5.2 | Fix bug if any |  |  | Đạt | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 5.5.3 | Run one-time manual result |  |  | Đạt | 2024-07-12 | 1 | 2024-07-12 | 40 days | Not started | bar: WEEK 13 (03/06 - 09/06) M
1 | 6 | MONITORING & MAINTAIN |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
2 | 6.1 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 6.1.1 | Model evaluation pipeline |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 6.1.2 | Tunning data preparation pipeline |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 6.1.3 | Tunning model pipeline |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 6.1.4 | Build report to track model performance |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 6.2 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 6.2.1 | Monitor operation system |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 6.2.2 | Repository git maintain |  |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | 6.3 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M; WEEK 16 (24/06 - 30/06) Sa to WEEK 16 (24/06 - 30/06) Su; WEEK 16 (01/07 - 07/07) Sa to WEEK 16 (01/07 - 07/07) Su; WEEK 16 (08/07 - 14/07) Sa to WEEK 16 (08/07 - 14/07) Su
3 | 6.3.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | 6.3.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. |  | Đạt |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦

## News system
NEWS SYSTEM PLAN | [8 empty] | 12 | 2024-06-03 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2024-05-27 to 2024-07-21
TASK ID | TASK TITLE | NOTE | TASK OWNER | SPRINT | START DATE | DURATION | END DATE | TIME LEFT | STATUS | 2024-05-27: WEEK 12 (27/05 - 02/06); 2024-06-03: WEEK 13 (03/06 - 09/06); 2024-06-10: WEEK 14 (10/06 - 16/06); 2024-06-17: WEEK 15 (17/06 - 23/06); 2024-06-24: WEEK 16 (24/06 - 30/06); 2024-07-01: WEEK 17 (01/07 - 07/07); 2024-07-08: WEEK 18 (08/07 - 14/07); 2024-07-15: WEEK 19 (15/07 - 21/07)
[10 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
A. | NEWS AI CLASSIFICATION |  | Đạt |  | 2024-03-18 | 45 | 2024-05-17 | Expired | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  | 2024-03-15 | 2 | 2024-03-18 | Done | Done | bar: WEEK 13 (03/06 - 09/06) M
1.2 | Design model architecture | 1. Training: Components + GCP service + algorithms + backtest pipeline 2. Deploy + production: Data pipeline + platform + dockerize + monitoring 3. Tuning model pipeline | Đạt |  | 2024-03-19 | 1 | 2024-03-19 | Done | Done | bar: WEEK 13 (03/06 - 09/06) M
1.3 | Plan how to labeling news data for classification model |  | Đạt |  | 2024-03-21 | 1 | 2024-03-21 | Done | Done | bar: WEEK 13 (03/06 - 09/06) M
1.4 | Setup resources & environments |  | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
2.1 | Data collection |  | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.2 | Train data preparation | contents, labels (classification), title, tags, categories, brief | Đạt |  | 2024-03-25 | 1 | 2024-03-25 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.3 | Preprocess the news articles | tokenization, removing stop words, and stemming | Đạt |  | 2024-04-01 | 4 | 2024-04-04 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4 | Label the articles - write method and plan |  | Đạt |  | 2024-03-26 | 1 | 2024-03-26 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.1 | - by category | refactor category | Đạt |  | 2024-03-27 | 3 | 2024-03-29 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.2 | - by sector | manual labeling | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.3 | - by sentiment | manual labeling | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
3.1 | Data train/test split |  | Đạt |  | 2024-04-04 | 1 | 2024-04-04 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.2 | Data loader pipeline |  | Đạt |  | 2024-04-04 | 2 | 2024-04-05 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.3 | Data preprocessing |  | Đạt |  | 2024-04-08 | 4 | 2024-04-11 | Expired | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4 | Build classification model - by category |  | Đạt |  |  | 7 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4.1 | - Build architecture |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4.2 | - Train model |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4.3 | - Evaluation model |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4.4 | - Tuning model |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4.5 | - Ensemble model |  | Đạt |  |  | 0 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6.2 | - Train model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
3.6.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Pending | bar: WEEK 13 (03/06 - 09/06) M
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
4.1 | Dockerize model |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Build data pipeline |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Deploy model and run service |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.1 | API development (optional) |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Testing |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Build log system + monitoring |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.2 | Tunning data preparation pipeline |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.3 | Tunning model pipeline |  | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Monitor system |  | Đạt |  |  | 3 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Repository git maintain |  | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  | 2 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  | 1 |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
B. | CUSTOMER PREFERENCES |  | Đạt |  | 2024-05-20 | 25 | 2024-06-21 | 19 days | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
C. | NEWS RECOMMENDATION |  | Đạt |  | 2024-06-24 | 30 | 2024-08-02 | 61 days | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
C. | NEWS SUMMARIZER |  | Đạt |  | 2024-08-05 | 20 | 2024-08-30 | 89 days | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1 | Define Requirements & Architecture | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
1.1 | Research algorithms and write requirements |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
1.2 | Design model architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2 | Data Processing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
2.1 | Data collection |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.2 | Train data preparation |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.3 | Preprocess the news articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4 | Label the articles |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.1 | - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.2 | - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
2.4.3 | - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3 | Model development | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
3.1 | Setup resources & environments |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.2 | Data train/test split |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.3 | Data loader pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.4 | Data preprocessing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by category |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sector |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5 | Build classification model - by sentiment |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.1 | - Build architecture |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.2 | - Train model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.3 | - Evaluation model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.4 | - Tuning model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
3.5.5 | - Ensemble model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4 | Deployment | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
4.1 | Dockerize model |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Build data pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Deploy model and run service |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.1 | API development (optional) |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.2 | Testing |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
4.3 | Build log system + monitoring |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5 | Tuning model | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
5.1 | Model evaluation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.2 | Tunning data preparation pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
5.3 | Tunning model pipeline |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Maintain and updates | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Monitor system |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Repository git maintain |  | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6 | Documentation and knowledge sharing | [6 empty] | No Info | Not started | bar: WEEK 12 (27/05 - 02/06) M to WEEK 19 (15/07 - 21/07) Su
6.1 | Document the entire process | Including data preprocessing, model training, deployment steps, and maintenance procedures | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
6.2 | Share knowledge | Share knowledge within your team or community to facilitate collaboration and future development efforts. | Đạt |  |  |  |  | No Info | Not started | bar: WEEK 13 (03/06 - 09/06) M
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
Note on C8: Khong Tien Dat: 1. Training: Components + GCP service + algorithms + backtest pipeline 2. Deploy + production: Data pipeline + platform + dockerize + monitoring 3. Tuning model pipeline